## Sheet1
Task/Phase | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8
Requirements Analysis | bar: Week 1 to Week 2
Define functional requirements | bar: Week 1
Define non-functional requirements | bar: Week 1
Validate requirements | bar: Week 1 to Week 2
Design Phase | bar: Week 2 to Week 3
System design | bar: Week 2 to Week 3
User interface design | bar: Week 3 to Week 4
Algorithm design | bar: Week 2 to Week 3
Implementation | bar: Week 3 to Week 4
Backend development | bar: Week 3 to Week 4
Frontend development (CLI/GUI) | bar: Week 4 to Week 5
Integration | bar: Week 5
Testing and Debugging | bar: Week 6 to Week 7
Unit testing | bar: Week 6
Integration testing | bar: Week 6
User testing | bar: Week 7
Security testing | bar: Week 7
Deployment | bar: Week 7 to Week 8
Packaging | bar: Week 7
Documentation | bar: Week 7
Distribution | bar: Week 8
Maintenance | bar: Week 8
Bug fixes | bar: Week 8
Feature upgrades | bar: Week 8